## Sprint 1 Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | PRIORITY | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
Find best hosting platform | 13 | Stuart | HIGH | Completed
Tasks' list can be found on GitHub | [5 empty] | 6 | 7
As a developer, I want to be able to see the end product I am trying to reach, So that I can be sure I am creating the page as intended. | 5 | Stuart, Neil | HIGH | Completed
Tasks' list can be found on GitHub | [5 empty] | 5
As a Customer, I want to be able to sign into my dashboard with the correct permissions, So that I have the functionality needed to do my job. | 20 | Laura, Gregor | HIGH | Completed
Tasks' list can be found on GitHub | [6 empty] | 12 | 8
As a developer I want to be able to have an initial page to add my features into. So that I can be sure I am working on the same file as my teammates. | 3 | Neil | HIGH | Completed
Tasks' list can be found on GitHub | [6 empty] | 3
As a Customer, I would like to see some information on the title bar of the app, So that I can be sure I am in the right dashboard, and account and that the statuses are up to date | 5 | Stuart | HIGH | Completed
Tasks' list can be found on GitHub | [7 empty] | 5
As a customer, I want to be able to see my dashboard on my phone, So that I can monitor my services from anywhere. | 3 | Stuart | LOW | Completed
Tasks' list can be found on GitHub | [8 empty] | 3
As a developer, I want to have the items I need to add backend functionality to in place, So that I can focus solely on my backend task. | 5 | Neil | MEDIUM | Completed
Tasks' list can be found on GitHub | [6 empty] | 5
As a Compliance Manager, I want to be able to easily add an exception to a rule, So that I can quickly fix any non-compliance issues that I want to get around. | 13 | Neil | HIGH | Completed
Tasks' list can be found on GitHub | [5 empty] | 3 | 5 | 5
As a customer, I want to be able to see the status indicator indicating the correct colour, So that I may quickly see if a service is compliant or non-compliant. | 13 | Stuart | HIGH | Completed
Tasks' list can be found on GitHub | [5 empty] | 6 | 7
As a customer, I want to be able to see the status of all of my services in accordance with my selected rule, So that I can individually see the compliance of all of my services within the rule. | 20 | Stuart | HIGH | Completed
Tasks' list can be found on GitHub | [7 empty] | 10 | 10
As a customer, I want to be able to see a list of all the rules I am following, So that I can easily see visually which rules I am compliant with. | 20 | Laura | HIGH | Completed
Tasks' list can be found on GitHub | [7 empty] | 12 | 8
TOTAL | 107 |  |  |  | 0 | 14 | 32 | 40 | 21
[5 empty] | 107 | 93 | 61 | 21 | 0

## Sprint 2 Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | PRIORITY | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
As a compliance manager I want to be able to add a new exception So that I can allow my cloud service to run ignoring the non-compliance flag. | 20 | Laura | HIGH | Completed
Tasks' list can be found on GitHub | [5 empty] | 5 | 5 | 5 | 5
As a compliance manager I want to be able to suspend exceptions So that I can check the status of a cloud service without the exception. | 20 | Stuart | MEDIUM | Completed
Tasks' list can be found on GitHub | [5 empty] | 10 | 10
As a customer, I want to be able to see a visual representation of my compliance, So that I can quickly tell what percentage of my services are compliant. | 5 | Neil | MEDIUM | Completed
Tasks' list can be found on GitHub |  |  |  |  | 5
As a customer, I want to be able to filter rules by their compliant/non-compliant status, So that I can easily find the rules and resources that need to have Exceptions added. | 13 | Stuart | HIGH | Completed
Tasks' list can be found on GitHub | [7 empty] | 6 | 7
As a Compliance Manager/Compliance Auditor, I want to know when a review date is approaching beforehand, So that I can look into whether the exception is still needed and review it before there is a problem. | 20 | Neil | MEDIUM | Completed
Tasks' list can be found on GitHub |  |  |  |  | 10 | 10
As a customer, I want to only see relevant resources the rule applies to, So that I can save time by not seeing resources that don't apply. | 3 | Stuart | HIGH | Completed
Tasks' list can be found on GitHub |  |  |  |  | 3
As a customer, I want to be able to quickly see my upcoming review dates on the dashboard, So that I can stay on top of my reviews. | 13 | Neil | MEDIUM | Completed
Tasks' list can be found on GitHub | [6 empty] | 6 | 7
As a customer, I want to see the pie chart of my compliance first on my phone, So that I can quickly see how compliant my resources are. | 3 | Stuart | LOW | Completed
Tasks' list can be found on GitHub |  |  |  |  | 3
As a customer, I want to be able to see if the resource has an exception, So that I can know if it is compliant because of an exception. | 5 | Stuart | MEDIUM | Completed
Tasks' list can be found on GitHub | [6 empty] | 5
As a customer, I want to be able to see the number of non-compliant issues under a rule, So that I can see exactly where most of my non-compliance lies. | 5 | Euan | MEDIUM | Completed
Tasks' list can be found on GitHub | [8 empty] | 5
TOTAL | 87 |  |  |  | 21 | 20 | 21 | 13 | 12
|  |  |  | 87 | 66 | 46 | 25 | 12 | 0

## Sprint 3 Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | PRIORITY | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
As a Compliance Auditor, I want to have access to only what I need, so that I only see what I need to and cannot perform extra operations. | 5 | Gregor | HIGH | Completed
5
As a Compliance Manager, I want to have: create, update and suspend access for exceptions, so that I can manage the exceptions on my cloud services. | 5 | Gregor | HIGH | Completed
5
As a customer, I want to be able to login to my company dashboard with my role So that I can see the correct view of my companies dashboard | 13 | Gregor, Euan | HIGH | Completed
[5 empty] | 7 | 6
As a Compliance Manager/Compliance Auditor, I want to be able to re-check the compliance of my services, So that I can be sure that the compliance report is up-to-date. | 5 | Stuart | MEDIUM | Completed
5
As a Compliance Manager, I want to be able to review my expiring exceptions, So that I can stay on top of my resources exceptions. | 20 | Neil, Stuart | HIGH | Completed
[5 empty] | 10 | 10
As a customer, I want to be able to see which rule has which ID So that I can easily identify which resource under which rule I am adding an exception review to. | 3 | Neil | MEDIUM | Completed
3
As a customer, I want to be able to see if the resource has any active exceptions, So that I can be confident that its status is/isn't because of any exceptions. | 3 | Stuart | HIGH | Completed
3
As a customer, I want to be able to select from a set list of values or choose my own, So that I can quickly select a timeframe or choose a longer one myself. | 20 | Laura | MEDIUM | Completed
[5 empty] | 13 | 7
As a customer, I want to be able to see a short description of what the rule is, So that I can better understand exactly what the "compliance" I am seeing is. | 3 | Stuart | MEDIUM | Completed
3
As a customer, I want to know if a full audit log of non-compliance is being tracked in my database, So that I can request this data if an issue arises and see an audit log of exceptions. | 13 | Laura | HIGH | Completed
[6 empty] | 7 | 6
As a user, I would like to see any exceptions that have expired without review, So that I can formally review them and re-enable them if necessary. | 13 | Neil | MEDIUM | Completed
[6 empty] | 3 | 10
As a user, I want to have my login details securely stored, So that it would not be hacked. | 5 | Laura | HIGH | Completed
5
| 108 |  |  |  | 36 | 33 | 26 | 13
|  |  |  | 108 | 72 | 39 | 13 | 0

## INDEX
Github Labels | Story Points
Large | 20
Medium | 13
Small | 5
Tiny | 2
Fibonacci sequence numbers to represent priority labels used in github