## Information from client
Information from client | Further notes
Create a Compliance Summary Dashboard | - Shows top-level summary of a non-compliance status rule - Allows a “Compliance Rule Detailed Report” to be viewed
Use a database on the backend to deal with the processing of data | Create tables according to the provided ER diagram by the client
User roles required | Site views are required for the following roles: - Compliance Auditor - Compliance Manager
Compliance Auditor | - Compliance Auditor: Can view Compliance Summary Dashboard, Compliance Rule Detailed View, Exceptions with justifications, review date and name of exception setter
Compliance Manager | - Compliance Manager: Can view Compliance Summary dashboard, Compliance Rule Detailed Report & Create, Read, Update, Suspend and view any exception including the justification, next review date and name of exception setter (cannot delete exception as would impact non-repudiation)
Compliance Rule Detailed Report | Provides the status of the cloud based resources compliance of the rule selected, Client requested a rule with a dropdown menu that then shows the compliance of every service underneath that rule according to that rule
Compliance manager actions | - Set exceptions that allows a non-compliant resource to run for x amount of time, this time must be stored in persistent data storage and review requested at end of time. - Exception non-repudiation, any exceptions added must be logged for auditing. When an exception is updated a new exception record must be stored for that specific cloud resource.
Exception status | When an exception has been set then the summary and report must both show compliant until the review date has passed.
Exception information to be stored/displayed | The justification, next review date and name of the Compliance manager that issued the exception must be visible to Compliance Auditors and Compliance Managers
Authentication | Web app can authenticate and authorize users based on role. Customer MUST not see other customers information
Expected output | - A working prototype of the web app. - GitHub must be used (or other SCM) - Must use a Continuous Integration (CI) pipeline - (Web app does not have to be built using AWS)
After meeting #1 with client
Layout | Pie chart should appear on top of the rules in mobile view and the rules should be sorted so that they are grouped by type and any non-compliant rules show first
Filtering resources | Only resources that follow the rule should appear undereneath the rule. Client also emphasised the importance of filtering by non-compliant to only show the problems and cut out the "noise"

## DOD
Definition of done
App functions as intended
All buttons can be pushed
All actions give expected results
App scales to mobile size
No elements go off the screen
Database operations can be performed as expected

## Front-End
User Stories | Order | Value | User-Facing Test of done
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/8 | Sprint 1 | On Github | On Github
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/16 | Sprint 1 | On Github | On Github
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/20 | Sprint 1 | On Github | On Github
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/40 | Sprint 1 | On Github | On Github
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/19 | Sprint 1 | On Github | On Github
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/22 | Sprint 1 | On Github | On Github
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/24 | Sprint 1 | On Github | On Github
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/27 | Sprint 1 | On Github | On Github
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/30 | Sprint 1 | On Github | On Github
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/32 | Sprint 1 | On Github | On Github
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/17 | Sprint 1 | On Github | On Github
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/42 | Sprint 1 | On Github | On Github
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/45 | Sprint 2 | On Github | On Github
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/46 | Sprint 2 | On Github | On Github
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/47 | Sprint 2 | On Github | On Github
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/18 | Sprint 2 | On Github | On Github
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/54 | Sprint 2 | On Github | On Github
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/74 | Sprint 3 | On Github | On Github
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/63 | Sprint 3 | On Github | On Github
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/62 | Sprint 3 | On Github | On Github
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/59 | Sprint 3 | On Github | On Github
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/58 | Sprint 3 | On Github | On Github

## Back-End
User Stories | Order | Value | User-Facing Test of done
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/10 | Sprint 1 | On GitHub | On GitHub
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/33 | Sprint 1 | On GitHub | On GitHub
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/13 | Sprint 2 | On GitHub | On GitHub
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/14 | Sprint 2 | On GitHub | On GitHub
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/26 | Sprint 2 | On GitHub | On GitHub
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/44 | Sprint 2 | On GitHub | On GitHub
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/21 | Sprint 2 | On GitHub | On GitHub
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/12 | Sprint 3 | On GitHub | On GitHub
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/15 | Sprint 3 | On GitHub | On GitHub
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/11 | Sprint 3 | On GitHub | On GitHub
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/29 | Sprint 3 | On GitHub | On GitHub
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/53 | Sprint 3 | On GitHub | On GitHub
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/62 | Sprint 3 | On GitHub | On GitHub
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/63 | Sprint 3 | On GitHub | On GitHub
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/71 | Sprint 3 | On GitHub | On GitHub
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/74 | Sprint 3 | On GitHub | On GitHub
https://github.com/Stuflo19/Team-8-Industrial-Project/issues/81 | Sprint 3 | On GitHub | On GitHub